## Cover (1)
Metric Consulting Engineers & Architects Co.,Ltd. | Metric Consulting Engineers & Architects Co.,Ltd. |  |  |  |  | Document Number: TP-PM-DSN-006 | Document Type: TEMPLATE | Discipline: PMO
[6 empty] | Revision: 01 | Issue Date: 07-MAY-26 | Author: PKP
Drawing List
REVISIONS
| Rev. | Issued date | Created by | Reviewed by | Approved by | Remark
| 00 | 2025-09-17 | PKP | ANC | ANC | First issue
| 01 | 2026-05-07 | PKP | ANC | ANC | Add Create/Review/Approve's Position

## Cover(2)
PROJECT NAME LOCATION, PROVINCE, THAILAND | [6 empty] | Insert project name, project location, and client's company logo
Drawing List
DRAWING LIST
| Overall Drawing Progress (as of DD Mmm YY) | [5 empty] | To input progress for each deliverable submission (optional)
|  | Civil Works | 100%
|  | Architectural Works | 100%
|  | Structural Works | 100%
|  | Mechanical Works | 100%
|  | Electrical Works | 100%
To register revision of drawing list for each submission.
| No. | Description |  | By | Date | Remarks
DOCUMENT NUMBER |  |  |  | CREATED | REVIEWED | APPROVED
| 2XXX-PM-LST-02-Rx Drawing List |  |  | Name S. | Name S. | Name S. | Document project number. XXXX indicates Metric's project number. If a project number is 2023-21, XXXX is to be 2321.
|  |  |  | PCO | PM | PD
OWNER'S LOGO

## 1. CIVIL
PROJECT NAME LOCATION, PROVINCE, THAILAND
1. CIVIL | [10 empty] | Responsible
| Drawing List | [9 empty] | Leader | Execute | Draftman | DD weight | 50DD |  | 100DD |  | Total Progress
Drawing number |  |  | Descriptions |  | Rv. |  |  | Size | type | Remark |  |  |  |  | Plan | Actual | Plan | Actual
[5 empty] | dd MMM | dd MMM | dd MMM
General Drawing
18043-LM000 01105 | - | DDD |  | Plot Plan & Location Map | A | [5 empty] | AFC | AFC | KSB | 1 | 80% | 80% | 100% | 95% | 95%
18043-LM000 01105-P | - | DDD |  | Plot Plan & Location Map | A | [5 empty] | AFC | AFC | KSB | 1.5 | 60% | 60% | 100% | 90% | 90%
18043-LM000 01112 | - | DDD |  | Covered Passage Way (190-642) - Plans, Section and Detail | A | [5 empty] | AFC | AFC | KSB | 1.5 | 60% | 60% | 100% | 90% | 90%
18043-LM000 01113 | - | DDD |  | Covered Passage Way (190-642) - Elevations, Sections and Details | A | [5 empty] | AFC | AFC | KSB | 1.5 | 60% | 20% | 100% | 90% | 90%
18043-LMBME 01051 | - | DDD |  | Project Design Outline | [6 empty] | AFC | NPM | KSB | 2.5 | 80% | 60% | 100% | 90% | 90%
18043-LMBME 01052 | - | DDD |  | Abbreviation & Finihsing Material list | A | [5 empty] | AFC | NPM | KSB | 2.5 | 80% | 70% | 100% | 90% | 90%
18043-LMBME 01053 | - | DDD |  | BLDG. 646 & 191-1 Room Schedule | A | [5 empty] | AFC | NPM | KSB | 2.5 | 80% | 70% | 100% | 80% | 80%
18043-LMBME 01054 | - | DDD |  | #REF! | A
18043-LMBME 01055 | - | DDD |  | #REF! | A
18043-LMBME 01056 | - | DDD |  | #REF! | A | [5 empty] | AFC | NPM | KSB | 2.5 | 60% | 60% | 100% | 90% | 90%
18043-LMBME 01057 | - | DDD |  | BLDG. 646 & 191-1 & 191 - Fire Compartment & Evacuation Plan | A | [5 empty] | AFC | NPM | KSB | 2.5 | 30% | 60% | 100% | 90% | 90%
[11 empty] | AFC | NPM | KSB | 2.5 | 30% | 10% | 100% | 70% | 70%
18043-LMBMS 01101 | - | DDD |  | Typical Architectural Details Sheet 1 (Metal roof sheet) | A
18043-LMBMS 01102 | - | DDD |  | Typical Architectural Details Sheet 2 (Sandwich panel ) | A | [5 empty] | AFC | NPM | KSB | 1.5 | 60% | 60% | 100% | 90% | 90%
18043-LMBMS 01103 | - | DDD |  | Typical Architectural Details Sheet 3 (Protection , Handrail) | A | [5 empty] | AFC | NPM | KSB | 0.5 | 0% | 0% | 100% | 30% | 30%
18043-LMBMS 01104 | - | DDD |  | Typical Architectural Details Sheet 4 (Masonry Detail) | A | [5 empty] | AFC | NPM | KSB | 0.5 | 0% | 0% | 100% | 30% | 30%
18043-LMBMS 01104 | - | DDD |  | Typical Architectural Details Sheet 4 (Fire proof joint) | A | [5 empty] | AFC | NPM | KSB | 0.5 | 0% | 0% | 100% | 30% | 30%
[11 empty] | AFC | PTF | PMO | 1.5 | 30% | 70% | 100% | 80% | 80%
[11 empty] | AFC | PTF | PMO | 1 | 30% | 30% | 100% | 80% | 80%
|  |  |  | SUB-TOTAL GENERAL DRAWING DRAWINGS |  |  |  | 15 |  |  | AFC | PTF | PMO | 1 | 0% | 0% | 100% | 80% | 80%
[11 empty] | AFC | PTF | PMO | 1 | 0% | 0% | 100% | 50% | 50%
Building Name or Area Name 1 | [10 empty] | AFC | AFC | KSB | 1 | 0% | 40% | 100% | 50% | 50%
18043-LM646 01101 | - | DDD |  | Ground Floor Plan EL.+00 , Mezzanine 1A Floor Plan EL.+10.00 | A
18043-LM646 01102 | - | DDD |  | Mezzanine 1B Floor Plan EL.+14.00 & 2nd Floor plan EL.+20.00 | A | [5 empty] | AFC | NPM | KSB | 1 | 60% | 60% | 100% | 90% | 90%
18043-LM646 01103 | - | DDD |  | Mezzanine 2A Floor Plan EL.+25.00 & 3rd Floor Plan EL.+30.00 | A | [5 empty] | AFC | NPM | KSB | 1.5 | 60% | 60% | 100% | 80% | 80%
18043-LM646 01104 | - | DDD |  | Roof Plan El.+36.00 | A
18043-LM646 01105 | - | DDD |  | Fire Compartment & Evacuation Plan | A
18043-LM646 01106 | - | DDD |  | Ground Floor Building Protection Plan | A | [5 empty] | AFC | NPM | KSB | 1 | 60% | 40% | 100% | 50% | 50%
18043-LM646 01107 | - | DDD |  | Ground Floor Process Clear Height Plan | A | [5 empty] | AFC | NPM | KSB | 1.5 | 60% | 0% | 100% | 90% | 90%
18043-LM646 01108 | - | DDD |  | Sections Sheet 1 | A | [5 empty] | AFC | NPM | KSB | 1 | 0% | 0% | 100% | 30% | 30%
18043-LM646 01109 | - | DDD |  | Sections Sheet 2 | A
18043-LM646 01110 | - | DDD |  | Sections Sheet 3 | A
18043-LM646 01111 | - | DDD |  | Elevations Sheet 1 | A | [5 empty] | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 95% | 95%
18043-LM646 01112 | - | DDD |  | Elevations Sheet 2 | A | [5 empty] | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 95% | 95%
[11 empty] | AFC | AFC | KSB | 1 | 30% | 30% | 100% | 95% | 95%
18043-LM646 01121 | - | DDD |  | Wall Section & Section Details sheet 1 | A
18043-LM646 01122 | - | DDD |  | Wall Section & Section Details sheet 2 | A
18043-LM646 01123 | - | DDD |  | Wall Section & Section Details sheet 3 | A | [5 empty] | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 95% | 95%
18043-LM646 01124 | - | DDD |  | Stair 646ST-1 Details | A | [5 empty] | AFC | AFC | KSB | 1 | 30% | 60% | 100% | 95% | 95%
18043-LM646 01125 | - | DDD |  | Stair 646ST-2 Details | A
18043-LM646 01126 | - | DDD |  | Stair 646ST-3,4 Details | A
18043-LM646 01127 | - | DDD |  | Door and Window Details | A | [5 empty] | AFC | AFC | KSB | 1 | 30% | 0% | 100% | 30% | 30%
18043-LM646 01128 | - | DDD |  | Enlarge Detail sheet 1 | A | [5 empty] | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 95% | 95%
18043-LM646 01129 | - | DDD |  | Enlarge Detail sheet 2 | A | [5 empty] | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 95% | 95%
[11 empty] | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 60% | 60%
[11 empty] | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 30% | 60%
|  |  |  | SUB-TOTAL BUILDING NAME OR AREA NAME 1 DRAWINGS |  |  |  | 21 |  |  | AFC | AFC | KSB | 2 | 60% | 60% | 100% | 30% | 60%
[11 empty] | AFC | AFC | KSB | 3 | 60% | 60% | 100% | 30% | 60%
Building Name or Area Name 2 | [10 empty] | AFC | AFC | KSB | 4 | 60% | 60% | 100% | 30% | 60%
[11 empty] | AFC | AFC | KSB | 5 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01101 | - | DDD |  | Steel Stair modification | A | [5 empty] | AFC | AFC | KSB | 6 | 60% | 60% | 100% | 30% | 60%
[11 empty] | AFC | AFC | KSB | 7 | 60% | 60% | 100% | 30% | 60%
[11 empty] | AFC | AFC | KSB | 8 | 60% | 60% | 100% | 30% | 60%
|  |  |  | SUB-TOTAL BUILDING NAME OR AREA NAME 2 DRAWINGS |  |  |  | 1 |  |  | AFC | AFC | KSB | 9 | 60% | 60% | 100% | 30% | 60%
Building Name or Area Name 3 | [10 empty] | AFC | AFC | KSB | 10 | 60% | 60% | 100% | 30% | 60%
[11 empty] | AFC | AFC | KSB | 11 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01101 | - | DDD |  | Ground Floor - Roof plans | A | [5 empty] | AFC | AFC | KSB | 12 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01102 | - | DDD |  | Sections Sheet 1 | A | [5 empty] | AFC | AFC | KSB | 13 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01103 | - | DDD |  | Elevations Sheet 1 | A | [5 empty] | AFC | AFC | KSB | 14 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01121 | - | DDD |  | Wall Section & Section Detail sheet 1 | A | [5 empty] | AFC | AFC | KSB | 15 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01122 | - | DDD |  | Stair 191-1ST-31 Detail | A | [5 empty] | AFC | AFC | KSB | 16 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01123 | - | DDD |  | Door and Window Details | A | [5 empty] | AFC | AFC | KSB | 17 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01124 | - | DDD |  | Enlarge Detail sheet 1 | A | [5 empty] | AFC | AFC | KSB | 18 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01125 | - | DDD |  | Enlarge Detail sheet 2 | A | [5 empty] | AFC | AFC | KSB | 19 | 60% | 60% | 100% | 30% | 60%
[14 empty] | 234 | 57.97% | 57.35% | 100% | 39.38% | 63.74%
|  |  |  | SUB-TOTAL BUILDING NAME OR AREA NAME 3 DRAWINGS |  |  |  | 8
|  |  |  | GRAND-TOTAL CIVIL DRAWINGS |  |  |  | 45
OWNER'S LOGO

## 2. ARCHITECTURAL
PROJECT NAME LOCATION, PROVINCE, THAILAND
2. ARCHITECTURAL | [10 empty] | Responsible
| Drawing List | [9 empty] | Leader | Execute | Draftman | DD weight | 50DD |  | 100DD |  | Total Progress
Drawing number |  |  | Descriptions |  | Rv. |  |  | Size | type | Remark |  |  |  |  | Plan | Actual | Plan | Actual
[5 empty] | dd MMM | dd MMM | dd MMM
General Drawing
18043-LM000 01105 | - | DDD |  | Plot Plan & Location Map | A | [5 empty] | AFC | AFC | KSB | 1 | 80% | 80% | 100% | 95% | 95%
18043-LM000 01105-P | - | DDD |  | Plot Plan & Location Map | A | [5 empty] | AFC | AFC | KSB | 1.5 | 60% | 60% | 100% | 90% | 90%
18043-LM000 01112 | - | DDD |  | Covered Passage Way (190-642) - Plans, Section and Detail | A | [5 empty] | AFC | AFC | KSB | 1.5 | 60% | 60% | 100% | 90% | 90%
18043-LM000 01113 | - | DDD |  | Covered Passage Way (190-642) - Elevations, Sections and Details | A | [5 empty] | AFC | AFC | KSB | 1.5 | 60% | 20% | 100% | 90% | 90%
18043-LMBME 01051 | - | DDD |  | Project Design Outline | [6 empty] | AFC | NPM | KSB | 2.5 | 80% | 60% | 100% | 90% | 90%
18043-LMBME 01052 | - | DDD |  | Abbreviation & Finihsing Material list | A | [5 empty] | AFC | NPM | KSB | 2.5 | 80% | 70% | 100% | 90% | 90%
18043-LMBME 01053 | - | DDD |  | BLDG. 646 & 191-1 Room Schedule | A | [5 empty] | AFC | NPM | KSB | 2.5 | 80% | 70% | 100% | 80% | 80%
18043-LMBME 01054 | - | DDD |  | #REF! | A
18043-LMBME 01055 | - | DDD |  | #REF! | A
18043-LMBME 01056 | - | DDD |  | #REF! | A | [5 empty] | AFC | NPM | KSB | 2.5 | 60% | 60% | 100% | 90% | 90%
18043-LMBME 01057 | - | DDD |  | BLDG. 646 & 191-1 & 191 - Fire Compartment & Evacuation Plan | A | [5 empty] | AFC | NPM | KSB | 2.5 | 30% | 60% | 100% | 90% | 90%
[11 empty] | AFC | NPM | KSB | 2.5 | 30% | 10% | 100% | 70% | 70%
18043-LMBMS 01101 | - | DDD |  | Typical Architectural Details Sheet 1 (Metal roof sheet) | A
18043-LMBMS 01102 | - | DDD |  | Typical Architectural Details Sheet 2 (Sandwich panel ) | A | [5 empty] | AFC | NPM | KSB | 1.5 | 60% | 60% | 100% | 90% | 90%
18043-LMBMS 01103 | - | DDD |  | Typical Architectural Details Sheet 3 (Protection , Handrail) | A | [5 empty] | AFC | NPM | KSB | 0.5 | 0% | 0% | 100% | 30% | 30%
18043-LMBMS 01104 | - | DDD |  | Typical Architectural Details Sheet 4 (Masonry Detail) | A | [5 empty] | AFC | NPM | KSB | 0.5 | 0% | 0% | 100% | 30% | 30%
18043-LMBMS 01104 | - | DDD |  | Typical Architectural Details Sheet 4 (Fire proof joint) | A | [5 empty] | AFC | NPM | KSB | 0.5 | 0% | 0% | 100% | 30% | 30%
[11 empty] | AFC | PTF | PMO | 1.5 | 30% | 70% | 100% | 80% | 80%
[11 empty] | AFC | PTF | PMO | 1 | 30% | 30% | 100% | 80% | 80%
|  |  |  | SUB-TOTAL GENERAL DRAWING DRAWINGS |  |  |  | 15 |  |  | AFC | PTF | PMO | 1 | 0% | 0% | 100% | 80% | 80%
[11 empty] | AFC | PTF | PMO | 1 | 0% | 0% | 100% | 50% | 50%
Building Name or Area Name 1 | [10 empty] | AFC | AFC | KSB | 1 | 0% | 40% | 100% | 50% | 50%
18043-LM646 01101 | - | DDD |  | Ground Floor Plan EL.+00 , Mezzanine 1A Floor Plan EL.+10.00 | A
18043-LM646 01102 | - | DDD |  | Mezzanine 1B Floor Plan EL.+14.00 & 2nd Floor plan EL.+20.00 | A | [5 empty] | AFC | NPM | KSB | 1 | 60% | 60% | 100% | 90% | 90%
18043-LM646 01103 | - | DDD |  | Mezzanine 2A Floor Plan EL.+25.00 & 3rd Floor Plan EL.+30.00 | A | [5 empty] | AFC | NPM | KSB | 1.5 | 60% | 60% | 100% | 80% | 80%
18043-LM646 01104 | - | DDD |  | Roof Plan El.+36.00 | A
18043-LM646 01105 | - | DDD |  | Fire Compartment & Evacuation Plan | A
18043-LM646 01106 | - | DDD |  | Ground Floor Building Protection Plan | A | [5 empty] | AFC | NPM | KSB | 1 | 60% | 40% | 100% | 50% | 50%
18043-LM646 01107 | - | DDD |  | Ground Floor Process Clear Height Plan | A | [5 empty] | AFC | NPM | KSB | 1.5 | 60% | 0% | 100% | 90% | 90%
18043-LM646 01108 | - | DDD |  | Sections Sheet 1 | A | [5 empty] | AFC | NPM | KSB | 1 | 0% | 0% | 100% | 30% | 30%
18043-LM646 01109 | - | DDD |  | Sections Sheet 2 | A
18043-LM646 01110 | - | DDD |  | Sections Sheet 3 | A
18043-LM646 01111 | - | DDD |  | Elevations Sheet 1 | A | [5 empty] | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 95% | 95%
18043-LM646 01112 | - | DDD |  | Elevations Sheet 2 | A | [5 empty] | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 95% | 95%
[11 empty] | AFC | AFC | KSB | 1 | 30% | 30% | 100% | 95% | 95%
18043-LM646 01121 | - | DDD |  | Wall Section & Section Details sheet 1 | A
18043-LM646 01122 | - | DDD |  | Wall Section & Section Details sheet 2 | A
18043-LM646 01123 | - | DDD |  | Wall Section & Section Details sheet 3 | A | [5 empty] | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 95% | 95%
18043-LM646 01124 | - | DDD |  | Stair 646ST-1 Details | A | [5 empty] | AFC | AFC | KSB | 1 | 30% | 60% | 100% | 95% | 95%
18043-LM646 01125 | - | DDD |  | Stair 646ST-2 Details | A
18043-LM646 01126 | - | DDD |  | Stair 646ST-3,4 Details | A
18043-LM646 01127 | - | DDD |  | Door and Window Details | A | [5 empty] | AFC | AFC | KSB | 1 | 30% | 0% | 100% | 30% | 30%
18043-LM646 01128 | - | DDD |  | Enlarge Detail sheet 1 | A | [5 empty] | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 95% | 95%
18043-LM646 01129 | - | DDD |  | Enlarge Detail sheet 2 | A | [5 empty] | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 95% | 95%
[11 empty] | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 60% | 60%
[11 empty] | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 30% | 60%
|  |  |  | SUB-TOTAL BUILDING NAME OR AREA NAME 1 DRAWINGS |  |  |  | 21 |  |  | AFC | AFC | KSB | 2 | 60% | 60% | 100% | 30% | 60%
[11 empty] | AFC | AFC | KSB | 3 | 60% | 60% | 100% | 30% | 60%
Building Name or Area Name 2 | [10 empty] | AFC | AFC | KSB | 4 | 60% | 60% | 100% | 30% | 60%
[11 empty] | AFC | AFC | KSB | 5 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01101 | - | DDD |  | Steel Stair modification | A | [5 empty] | AFC | AFC | KSB | 6 | 60% | 60% | 100% | 30% | 60%
[11 empty] | AFC | AFC | KSB | 7 | 60% | 60% | 100% | 30% | 60%
[11 empty] | AFC | AFC | KSB | 8 | 60% | 60% | 100% | 30% | 60%
|  |  |  | SUB-TOTAL BUILDING NAME OR AREA NAME 2 DRAWINGS |  |  |  | 1 |  |  | AFC | AFC | KSB | 9 | 60% | 60% | 100% | 30% | 60%
Building Name or Area Name 3 | [10 empty] | AFC | AFC | KSB | 10 | 60% | 60% | 100% | 30% | 60%
[11 empty] | AFC | AFC | KSB | 11 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01101 | - | DDD |  | Ground Floor - Roof plans | A | [5 empty] | AFC | AFC | KSB | 12 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01102 | - | DDD |  | Sections Sheet 1 | A | [5 empty] | AFC | AFC | KSB | 13 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01103 | - | DDD |  | Elevations Sheet 1 | A | [5 empty] | AFC | AFC | KSB | 14 | 60% | 60% | 100% | 30% | 60%
[11 empty] | AFC | AFC | KSB | 15 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01121 | - | DDD |  | Wall Section & Section Detail sheet 1 | A | [5 empty] | AFC | AFC | KSB | 16 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01122 | - | DDD |  | Stair 191-1ST-31 Detail | A | [5 empty] | AFC | AFC | KSB | 17 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01123 | - | DDD |  | Door and Window Details | A | [5 empty] | AFC | AFC | KSB | 18 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01124 | - | DDD |  | Enlarge Detail sheet 1 | A | [5 empty] | AFC | AFC | KSB | 19 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01125 | - | DDD |  | Enlarge Detail sheet 2 | A | [5 empty] | AFC | AFC | KSB | 20 | 60% | 60% | 100% | 30% | 60%
[14 empty] | 254 | 58.13% | 57.56% | 100% | 38.64% | 63.44%
|  |  |  | SUB-TOTAL BUILDING NAME OR AREA NAME 3 DRAWINGS |  |  |  | 8
|  |  |  | GRAND-TOTAL CIVIL DRAWINGS |  |  |  | 45
OWNER'S LOGO

## 3. STRUCTURAL
PROJECT NAME LOCATION, PROVINCE, THAILAND
3. STRUCTURAL | [10 empty] | Responsible
| Drawing List | [9 empty] | Leader | Execute | Draftman | DD weight | 50DD |  | 100DD |  | Total Progress
Drawing number |  |  | Descriptions |  | Rv. |  |  | Size | type | Remark |  |  |  |  | Plan | Actual | Plan | Actual
[5 empty] | dd MMM | dd MMM | dd MMM
General Drawing
18043-LMBMS 01501 | - | DDD |  | Typical Structural Details & General Notes Sheet 1 | A | [5 empty] | AFC | AFC | KSB | 0 | 80% | 80% | 100% | 95% | 95%
18043-LMBMS 01502 | - | DDD |  | Typical Structural Details & General Notes Sheet 2 | A | [5 empty] | AFC | AFC | KSB | 1 | 80% | 80% | 100% | 95% | 95%
18043-LMBMS 01503 | - | DDD |  | Typical Structural Details & General Notes Sheet 3 | A | [5 empty] | AFC | AFC | KSB | 1.5 | 60% | 60% | 100% | 90% | 90%
18043-LMBMS 01701 | - | DDD |  | Typical Steel Connection Sheet 1 | A | [5 empty] | AFC | AFC | KSB | 1.5 | 60% | 60% | 100% | 90% | 90%
18043-LMBMS 01702 | - | DDD |  | Typical Steel Connection Sheet 2 | A | [5 empty] | AFC | AFC | KSB | 1.5 | 60% | 20% | 100% | 90% | 90%
18043-LMBMS 01703 | - | DDD |  | Typical Steel Connection Sheet 3 | A | [5 empty] | AFC | AFC | KSB | 2.5 | 60% | 20% | 100% | 90% | 90%
18043-LMBME 01501 | - | DDD |  | Overall Demolition Floor Plan | A | [5 empty] | AFC | NPM | KSB | 2.5 | 80% | 60% | 100% | 90% | 90%
18043-LMBME 01502 | - | DDD |  | Demolition Floor Plan sheet1 | A | [5 empty] | AFC | NPM | KSB | 2.5 | 80% | 70% | 100% | 90% | 90%
18043-LMBME 01503 | - | DDD |  | Demolition Floor Plan sheet2 | A | [5 empty] | AFC | NPM | KSB | 2.5 | 80% | 70% | 100% | 80% | 80%
|  |  |  | SUB-TOTAL GENERAL DRAWING DRAWINGS |  |  |  | 9
Building Name or Area Name 1
18043-LM646 01501 | - | DDD |  | Piling Plan | A | [5 empty] | AFC | NPM | KSB | -1.5 | 60% | 60% | 100% | 90% | 90%
18043-LM646 01502 | - | DDD |  | Foundation Plan | A | [5 empty] | AFC | NPM | KSB | -0.5 | 60% | 60% | 100% | 90% | 90%
18043-LM646 01503 | - | DDD |  | 1 Floor Loading Plan | A | [5 empty] | AFC | NPM | KSB | 0.5 | 60% | 60% | 100% | 90% | 90%
18043-LM646 01504 | - | DDD |  | 1 Floor Framing Plan | A | [5 empty] | AFC | NPM | KSB | 1.5 | 60% | 60% | 100% | 90% | 90%
18043-LM646 01505 | - | DDD |  | 1.1 Floor Loading Plan | A | [5 empty] | AFC | NPM | KSB | 0.5 | 0% | 0% | 100% | 30% | 30%
18043-LM646 01506 | - | DDD |  | 1.1 Floor Framing Plan | A | [5 empty] | AFC | NPM | KSB | 0.5 | 0% | 0% | 100% | 30% | 30%
18043-LM646 01507 | - | DDD |  | 1.2 Floor Loading Plan | A | [5 empty] | AFC | NPM | KSB | 0.5 | 0% | 0% | 100% | 30% | 30%
18043-LM646 01508 | - | DDD |  | 1.2 Floor Framing Plan | A | [5 empty] | AFC | PTF | PMO | 1.5 | 30% | 70% | 100% | 80% | 80%
18043-LM646 01509 | - | DDD |  | 2 Floor Loading Plan | A | [5 empty] | AFC | PTF | PMO | 1 | 30% | 30% | 100% | 80% | 80%
18043-LM646 01510 | - | DDD |  | 2 Floor Framing Plan | A | [5 empty] | AFC | PTF | PMO | 1 | 0% | 0% | 100% | 80% | 80%
18043-LM646 01511 | - | DDD |  | 2.1 Floor Loading Plan | A | [5 empty] | AFC | PTF | PMO | 1 | 0% | 0% | 100% | 50% | 50%
18043-LM646 01512 | - | DDD |  | 2.1 Floor Framing Plan | A | [5 empty] | AFC | AFC | KSB | 1 | 0% | 40% | 100% | 50% | 50%
18043-LM646 01513 | - | DDD |  | 2.2 Floor Loading Plan | A | [5 empty] | AFC | AFC | KSB | 2 | 0% | 40% | 100% | 50% | 50%
18043-LM646 01514 | - | DDD |  | 2.2 Floor Framing Plan | A | [5 empty] | AFC | AFC | KSB | 3 | 0% | 40% | 100% | 50% | 50%
18043-LM646 01515 | - | DDD |  | Roof Slab Loading Plan | A | [5 empty] | AFC | NPM | KSB | 1 | 60% | 60% | 100% | 90% | 90%
18043-LM646 01516 | - | DDD |  | Roof Slab Framing Plan | A | [5 empty] | AFC | NPM | KSB | 1.5 | 60% | 60% | 100% | 80% | 80%
18043-LM646 01517 | - | DDD |  | Top Roof Loading Plan | A | [5 empty] | AFC | NPM | KSB | 2.5 | 60% | 60% | 100% | 80% | 80%
18043-LM646 01518 | - | DDD |  | Top Roof Framing Plan | A | [5 empty] | AFC | NPM | KSB | 3.5 | 60% | 60% | 100% | 80% | 80%
18043-LM646 01519 | - | DDD |  | Framing Elevation Sheet1 | A | [5 empty] | AFC | NPM | KSB | 1 | 60% | 40% | 100% | 50% | 50%
18043-LM646 01520 | - | DDD |  | Framing Elevation Sheet2 | A | [5 empty] | AFC | NPM | KSB | 1.5 | 60% | 0% | 100% | 90% | 90%
18043-LM646 01521 | - | DDD |  | Framing Elevation Sheet3 | A | [5 empty] | AFC | NPM | KSB | 1 | 0% | 0% | 100% | 30% | 30%
18043-LM646 01522 | - | DDD |  | Framing Elevation Sheet4 | A | [5 empty] | AFC | NPM | KSB | 2 | 0% | 0% | 100% | 30% | 30%
18043-LM646 01531 | - | DDD |  | Foundation Details Sheet1 | A | [5 empty] | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 95% | 95%
18043-LM646 01532 | - | DDD |  | Foundation Details Sheet2 | A | [5 empty] | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 95% | 95%
18043-LM646 01533 | - | DDD |  | Foundation Details Sheet3 | A | [5 empty] | AFC | AFC | KSB | 1 | 30% | 30% | 100% | 95% | 95%
18043-LM646 01534 | - | DDD |  | Foundation Details Sheet4 | A | [5 empty] | AFC | AFC | KSB | 2 | 30% | 30% | 100% | 95% | 95%
18043-LM646 01541 | - | DDD |  | Ground Floor Slab Reinforcement Plan Sheet1 | A | [5 empty] | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 95% | 95%
18043-LM646 01542 | - | DDD |  | Ground Floor Slab Reinforcement Plan Sheet2 | A | [5 empty] | AFC | AFC | KSB | 1 | 30% | 60% | 100% | 95% | 95%
18043-LM646 01543 | - | DDD |  | 2 Floor Slab Reinforcement Plan Sheet1 | A | [5 empty] | AFC | AFC | KSB | 2 | 30% | 60% | 100% | 95% | 95%
18043-LM646 01544 | - | DDD |  | 2 Floor Slab Reinforcement Plan Sheet2 | A | [5 empty] | AFC | AFC | KSB | 3 | 30% | 60% | 100% | 95% | 95%
18043-LM646 01545 | - | DDD |  | Roof Slab Reinforcement Details | A | [5 empty] | AFC | AFC | KSB | 1 | 30% | 0% | 100% | 30% | 30%
18043-LM646 01546 | - | DDD |  | Slab Reinforcement Sections Sheet1 | A | [5 empty] | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 95% | 95%
18043-LM646 01547 | - | DDD |  | Slab Reinforcement Sections Sheet2 | A | [5 empty] | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 95% | 95%
18043-LM646 01551 | - | DDD |  | Slab Reinforcement Continuity Typical Details Sheet 1 | A | [5 empty] | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01552 | - | DDD |  | Slab Reinforcement Continuity Typical Details Sheet 2 | A | [5 empty] | AFC | AFC | KSB | 2 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01561 | - | DDD |  | RC Miscellaneous Details Sheet1 | A | [5 empty] | AFC | AFC | KSB | 4 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01562 | - | DDD |  | RC Miscellaneous Details Sheet2 | A | [5 empty] | AFC | AFC | KSB | 5 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01701 | - | DDD |  | Steel Stair Details Sheet1 | A | [5 empty] | AFC | AFC | KSB | 7 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01702 | - | DDD |  | Steel Stair Details Sheet2 | A | [5 empty] | AFC | AFC | KSB | 8 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01711 | - | DDD |  | Steel Stair Connection Details Sheet1 | A | [5 empty] | AFC | AFC | KSB | 10 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01721 | - | DDD |  | Lift Details Sheet 1 | A | [5 empty] | AFC | AFC | KSB | 12 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01722 | - | DDD |  | Lift Details Sheet 2 | A | [5 empty] | AFC | AFC | KSB | 13 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01731 | - | DDD |  | Steel Miscellaneous Details Sheet1 | A | [5 empty] | AFC | AFC | KSB | 15 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01732 | - | DDD |  | Steel Miscellaneous Details Sheet2 | A | [5 empty] | AFC | AFC | KSB | 16 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01741 | - | DDD |  | Column Baseplate Details Sheet1 | A | [5 empty] | AFC | AFC | KSB | 18 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01742 | - | DDD |  | Column Baseplate Details Sheet2 | A | [5 empty] | AFC | AFC | KSB | 19 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01743 | - | DDD |  | Column Baseplate Details Sheet3 | A | [5 empty] | AFC | AFC | KSB | 20 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01744 | - | DDD |  | Column Baseplate Details Sheet4 | A | [5 empty] | AFC | AFC | KSB | 21 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01751 | - | DDD |  | Built-Up Section | A | [5 empty] | AFC | AFC | KSB | 23 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01752 | - | DDD |  | Steel Connection Details Sheet 1 | A | [5 empty] | AFC | AFC | KSB | 24 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01753 | - | DDD |  | Steel Connection Details Sheet 2 | A | [5 empty] | AFC | AFC | KSB | 25 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01754 | - | DDD |  | Steel Connection Details Sheet 3 | A | [5 empty] | AFC | AFC | KSB | 26 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01755 | - | DDD |  | Steel Connection Details Sheet 4 | A | [5 empty] | AFC | AFC | KSB | 27 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01761 | - | DDD |  | Typical X-bracing Details Sheet 1 | A | [5 empty] | AFC | AFC | KSB | 29 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01762 | - | DDD |  | Typical X-bracing Details Sheet 2 | A | [5 empty] | AFC | AFC | KSB | 30 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01771 | - | DDD |  | Steel Beam To Steel Beam Connection Details Sheet 1 | A | [5 empty] | AFC | AFC | KSB | 32 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01772 | - | DDD |  | Steel Beam To Steel Beam Connection Details Sheet 2 | A | [5 empty] | AFC | AFC | KSB | 33 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01781 | - | DDD |  | Specific Steel Connection Details Sheet1 | A | [5 empty] | AFC | AFC | KSB | 35 | 60% | 60% | 100% | 30% | 60%
18043-LM646 01782 | - | DDD |  | Specific Steel Connection Details Sheet2 | A | [5 empty] | AFC | AFC | KSB | 36 | 60% | 60% | 100% | 30% | 60%
|  |  |  | SUB-TOTAL BUILDING NAME OR AREA NAME 1 DRAWINGS |  |  |  | 60
Building Name or Area Name 2
18043-LM191-1 01501 | - | DDD |  | Piling Plan | A | [5 empty] | AFC | AFC | KSB | 41 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01502 | - | DDD |  | Foundation Plan | A | [5 empty] | AFC | AFC | KSB | 42 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01503 | - | DDD |  | Ground Floor Loading Plan | A | [5 empty] | AFC | AFC | KSB | 43 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01504 | - | DDD |  | Ground Floor Framing Plan | A | [5 empty] | AFC | AFC | KSB | 44 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01505 | - | DDD |  | 2nd Floor Loading Plan | A | [5 empty] | AFC | AFC | KSB | 45 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01506 | - | DDD |  | 2nd Floor Framing Plan | A | [5 empty] | AFC | AFC | KSB | 46 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01507 | - | DDD |  | 3rd Floor Loading Plan | A | [5 empty] | AFC | AFC | KSB | 47 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01508 | - | DDD |  | 3rd Floor Framing Plan | A | [5 empty] | AFC | AFC | KSB | 48 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01509 | - | DDD |  | 4th Floor Loading Plan | A | [5 empty] | AFC | AFC | KSB | 49 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01510 | - | DDD |  | 4th Floor Framing Plan | A | [5 empty] | AFC | AFC | KSB | 50 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01511 | - | DDD |  | Roof Slab Loading Plan | A | [5 empty] | AFC | AFC | KSB | 51 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01512 | - | DDD |  | Roof Slab Framing Plan | A | [5 empty] | AFC | AFC | KSB | 52 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01513 | - | DDD |  | Framing Elevation Sheet1 | A | [5 empty] | AFC | AFC | KSB | 53 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01514 | - | DDD |  | Framing Elevation Sheet2 | A | [5 empty] | AFC | AFC | KSB | 54 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01521 | - | DDD |  | Foundation Details Sheet1 | A | [5 empty] | AFC | AFC | KSB | 56 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01522 | - | DDD |  | Foundation Details Sheet2 | A | [5 empty] | AFC | AFC | KSB | 57 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01531 | - | DDD |  | Ground Floor Slab Reinforcement Plan Sheet1 | A | [5 empty] | AFC | AFC | KSB | 59 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01532 | - | DDD |  | Ground Floor Slab Reinforcement Plan Sheet2 | A | [5 empty] | AFC | AFC | KSB | 60 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01533 | - | DDD |  | 2nd Floor Slab Reinforcement Plan | A | [5 empty] | AFC | AFC | KSB | 61 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01534 | - | DDD |  | 3rd Floor Slab Reinforcement Plan | A | [5 empty] | AFC | AFC | KSB | 62 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01535 | - | DDD |  | 4th Floor Slab Reinforcement Plan | A | [5 empty] | AFC | AFC | KSB | 63 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01536 | - | DDD |  | Roof Slab Reinforcement Details | A | [5 empty] | AFC | AFC | KSB | 64 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01537 | - | DDD |  | Slab Reinforcement Sections Sheet1 | A | [5 empty] | AFC | AFC | KSB | 65 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01541 | - | DDD |  | Slab Reinforcement Continuity Typical Details Sheet 1 | A | [5 empty] | AFC | AFC | KSB | 67 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01551 | - | DDD |  | RC Miscellaneous Details Sheet1 | A | [5 empty] | AFC | AFC | KSB | 69 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01552 | - | DDD |  | RC Miscellaneous Details Sheet2 | A | [5 empty] | AFC | AFC | KSB | 70 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01701 | - | DDD |  | Steel Stair Details Sheet1 | A | [5 empty] | AFC | AFC | KSB | 72 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01711 | - | DDD |  | Steel Stair Connection Details Sheet1 | A | [5 empty] | AFC | AFC | KSB | 74 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01721 | - | DDD |  | Lift Details Sheet 1 | A | [5 empty] | AFC | AFC | KSB | 76 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01731 | - | DDD |  | Steel Miscellaneous Details Sheet1 | A | [5 empty] | AFC | AFC | KSB | 78 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01741 | - | DDD |  | Column Baseplate Details Sheet1 | A | [5 empty] | AFC | AFC | KSB | 80 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01742 | - | DDD |  | Column Baseplate Details Sheet2 | A | [5 empty] | AFC | AFC | KSB | 81 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01751 | - | DDD |  | Steel Connection Details Sheet 1 | A | [5 empty] | AFC | AFC | KSB | 83 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01752 | - | DDD |  | Steel Connection Details Sheet 2 | A | [5 empty] | AFC | AFC | KSB | 84 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 01753 | - | DDD |  | Steel Connection Details Sheet 3 | A | [5 empty] | AFC | AFC | KSB | 85 | 60% | 60% | 100% | 30% | 60%
|  |  |  | SUB-TOTAL BUILDING NAME OR AREA NAME 2 DRAWINGS |  |  |  | 35
Building Name or Area Name 3
18043-LM520 01501 | - | DDD |  | Modification Work Details Sheet 1 | A | [5 empty] | AFC | AFC | KSB | 91 | 60% | 60% | 100% | 30% | 60%
18043-LM520 01502 | - | DDD |  | Modification Work Details Sheet 2 | A | [5 empty] | AFC | AFC | KSB | 92 | 60% | 60% | 100% | 30% | 60%
[14 empty] | 2634 | 60% | 60% | 100% | 30% | 60%
|  |  |  | SUB-TOTAL BUILDING NAME OR AREA NAME 3 DRAWINGS |  |  |  | 2
|  |  |  | GRAND-TOTAL CIVIL DRAWINGS |  |  |  | 106
OWNER'S LOGO

## 4. MECHANICAL
PROJECT NAME LOCATION, PROVINCE, THAILAND
4. MECHANICAL | [10 empty] | Responsible
| Drawing List | [9 empty] | Leader | Execute | Draftman | DD weight | 50DD |  | 100DD |  | Total Progress
Drawing number |  |  | Descriptions |  | Rv. |  |  | Size | type | Remark |  |  |  |  | Plan | Actual | Plan | Actual
[5 empty] | dd MMM | dd MMM | dd MMM
General Drawing
18043-LMBMS 08214 | - | DDD |  | Typical Details Sheet 1 | A |  |  | A0 |  |  | AFC | AFC | KSB | 0 | 80% | 80% | 100% | 95% | 95% | LMBMS 08214 Rv.7A Typical Details Sheet 1
18043-LMBMS 08215 | - | DDD |  | Typical Details Sheet 2 | A |  |  | A0 |  |  | AFC | AFC | KSB | 1 | 80% | 80% | 100% | 95% | 95% | LMBMS 08215 Rv.7A Typical Details Sheet 2
18043-LMBMS 08217 | - | DDD |  | Fire Door Operation Typical Details | A |  |  | A0 |  |  | AFC | AFC | KSB | 1.5 | 60% | 60% | 100% | 90% | 90% | LMBMS 08217 Rv.5 Fire Door Operation Typical Details
18043-LMBMS 08218 | - | DDD |  | Fire Protection Abbreviation and General Note | A |  |  | A0 |  |  | AFC | AFC | KSB | 1.5 | 60% | 60% | 100% | 90% | 90% | LMBMS 08218 Rv.4A Fire Protection Abbreviation and General Note
18043-LMBMS 08219 | - | DDD |  | Typical Details Sheet 3 | A |  |  | A0 |  |  | AFC | AFC | KSB | 1.5 | 60% | 20% | 100% | 90% | 90% | LMBMS 08219 Rv.3A Typical Details Sheet 3
18043-LMBMS 08311 | - | DDD |  | Typical Details Sheet 1 | A |  |  | A0 |  |  | AFC | AFC | KSB | 3.5 | 60% | 20% | 100% | 90% | 90% | LMBMS 08311 Rv.16 Typical Details Sheet 1
18043-LMBMS 08312 | - | DDD |  | Typical Details Sheet 2 | A |  |  | A0 |  |  | AFC | NPM | KSB | 2.5 | 80% | 60% | 100% | 90% | 90% | LMBMS 08312 Rv.16 Typical Details Sheet 2
18043-LMBMS 08313 | - | DDD |  | Typical Details Sheet 3 | A |  |  | A0 |  |  | AFC | NPM | KSB | 2.5 | 80% | 70% | 100% | 90% | 90% | LMBMS 08313 Rv.16 Typical Details Sheet 3
18043-LMBMS 08314 | - | DDD |  | Typical Details Sheet 4 | A |  |  | A0 |  |  | AFC | NPM | KSB | 2.5 | 80% | 70% | 100% | 80% | 80% | LMBMS 08314 Rv.16 Typical Details Sheet 4
18043-LMBMS 08315 | - | DDD |  | Typical Details Sheet 5 | A |  |  | A0 |  |  | AFC | NPM | KSB | 3.5 | 80% | 70% | 100% | 80% | 80% | LMBMS 08315 Rv.16 Typical Details Sheet 5
18043-LMBMS 08513 | - | DDD |  | Typical Details Sheet 1 | A |  |  | A0 |  |  | AFC | NPM | KSB | 5.5 | 80% | 70% | 100% | 80% | 80% | LMBMS 08513 Rv.13 Typical Details Sheet 1
18043-LMBMS 08514 | - | DDD |  | Typical Details Sheet 2 | A |  |  | A0 |  |  | AFC | NPM | KSB | 6.5 | 80% | 70% | 100% | 80% | 80% | LMBMS 08514 Rv.13 Typical Details Sheet 2
18043-LMBMS 08515 | - | DDD |  | Typical Details Sheet 3 | A |  |  | A0 |  |  | AFC | NPM | KSB | -1.5 | 60% | 60% | 100% | 90% | 90% | LMBMS 08515 Rv.13 Typical Details Sheet 3
18043-LMBMS 08517 | - | DDD |  | Fluids Abbreviation and General Note | A |  |  | A0 |  |  | AFC | NPM | KSB | -0.5 | 60% | 60% | 100% | 90% | 90% | LMBMS 08517 Rv.2 Fluids Abbreviation and General Note
18043-LMBMS 09301 | - | DDD |  | Control Unit and Wiring Typical Details Sheet 1 | A |  |  | A3 |  |  | AFC | NPM | KSB | 1.5 | 60% | 60% | 100% | 90% | 90% | LMBMS 09301 Rv.6 Control Unit and Wiring Typical Details Sheet 1
18043-LMBMS 09302 | - | DDD |  | Control Unit and Wiring Typical Details Sheet 2 | A |  |  | A3 |  |  | AFC | NPM | KSB | 0.5 | 0% | 0% | 100% | 30% | 30% | LMBMS 09302 Rv.9 Control Unit and Wiring Typical Details Sheet 2
18043-LM000 08251 | - | DDD |  | Outside Building - Fire Protection System - Modification Plan | A |  |  | A0 |  |  | AFC | NPM | KSB | 0.5 | 0% | 0% | 100% | 30% | 30% | LM000 08251 Rv.10 Outside Building - Fire Protection System - Modification Plan | LMBME 08222 Rv.1C Overall Layout - Piping Outside Building Plan
18043-LMBME 08553 | - | DDD |  | Main Pipe Racks Fluid Distribution Diagram | A |  |  | A0 |  |  | AFC | PTF | PMO | 1 | 30% | 30% | 100% | 80% | 80% | LMBME 08553 Rv.18 Main Pipe Racks Fluid Distribution Diagram
|  |  |  | SUB-TOTAL GENERAL DRAWING DRAWINGS |  |  |  | 18
Building Name or Area Name 1
18043-LM000 08253 | - | DDD |  | Covered Passageway (190-642) - Fire Protection Plan & Sections | A |  |  | A0 |  |  | AFC | NPM | KSB | 1.5 | 60% | 60% | 100% | 80% | 80% | LM000 08253 Rv.3 Covered Passageway (190-642) - Fire Protection Plan & Sections
18043-LM000 08504 | - | DDD |  | Bladder Post, AFC Workshop & TBM Workshop - Piping Plans & Details | A |  |  | A0 |  |  | AFC | NPM | KSB | 2.5 | 60% | 60% | 100% | 80% | 80% | LM000 08504 Rv.3 Bladder Post, AFC Workshop & TBM Workshop - Piping Plans & Details
18043-LMBME 08560 | - | DDD |  | Main Pipes Rack Piping Layout | A |  |  | A0 |  |  | AFC | NPM | KSB | 3.5 | 60% | 60% | 100% | 80% | 80% | LMBME 08560 Rv.0c Main Pipes Rack Piping Layout
18043-LM103 08201 | - | DDD |  | Fire Water System - Plans | A |  |  | A0 |  |  | AFC | NPM | KSB | 1.5 | 60% | 0% | 100% | 90% | 90% | LM103 08201 Rv.5 Fire Water System - Plans
18043-LM103 08202 | - | DDD |  | Fire Water System - Sections | A |  |  | A0 |  |  | AFC | NPM | KSB | 1 | 0% | 0% | 100% | 30% | 30% | LM103 08202 Rv.2 Fire Water System - Sections
18043-LM103 08203 | - | DDD |  | LV2 Room - PLans & Diagram | A |  |  | A0 |  |  | AFC | NPM | KSB | 2 | 0% | 0% | 100% | 30% | 30% | LM103 08203 Rv.A LV2 Room - PLans & Diagram
18043-LM103 08301 | - | DDD |  | Air Conditioning & Ventilation System - P&I Diagram | A |  |  | A0 |  |  | AFC | NPM | KSB | 3 | 0% | 0% | 100% | 30% | 30% | LM103 08301 Rv.3 Air Conditioning & Ventilation System - P&I Diagram
18043-LM103 08302 | - | DDD |  | Air Conditioning & Ventilation System - Plan & Section | A |  |  | A0 |  |  | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 95% | 95% | LM103 08302 Rv.3 Air Conditioning & Ventilation System - Plan & Section
18043-LM263 08101 | - | DDD |  | Plumbing Plan and Details | A |  |  | A0 |  |  | AFC | AFC | KSB | 1 | 30% | 30% | 100% | 95% | 95% | LM263 08101 Rv.0 Plumbing Plan and Details
18043-LM263 08301 | - | DDD |  | Ventilation Plans | A |  |  | A0 |  |  | AFC | AFC | KSB | 2 | 30% | 30% | 100% | 95% | 95% | LM263 08301 Rv.0 Ventilation Plans
18043-LM642 08251 | - | DDD |  | Fire Protection Plan & Section | A |  |  | A0 |  |  | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 95% | 95% | LM642 08251 Rv.8 Fire Protection Plan & Section
18043-LM642 08302 | - | DDD |  | HVAC System - Plans & Sections | A |  |  | A0 |  |  | AFC | AFC | KSB | 1 | 30% | 60% | 100% | 95% | 95% | LM642 08302
18043-LM651 08201 | - | DDD |  | Fire Water System - Plan & Sections | A |  |  | A0 |  |  | AFC | AFC | KSB | 3 | 30% | 60% | 100% | 95% | 95% | LM651 08201 Rv.2 Fire Water System - Plan & Sections
18043-LM651 08301 | - | DDD |  | Air Conditioning System - Plan, Section And P&I Diagram | A |  |  | A0 |  |  | AFC | AFC | KSB | 1 | 30% | 0% | 100% | 30% | 30% | LM651 08301 Rv.2 Air Conditioning System - Plan, Section And P&I Diagram
18043-LM646 08201 | - | DDD |  | Fire Protection System - Ground Floor Sprinkler Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 95% | 95%
18043-LM646 08202 | - | DDD |  | Fire Protection System - Ground Floor Mezzanine Sprinkler Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 2 | 60% | 60% | 100% | 95% | 95%
18043-LM646 08203 | - | DDD |  | Fire Protection System - 2nd Floor Sprinkler Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 30% | 60%
18043-LM646 08204 | - | DDD |  | Fire Protection System - 2nd Floor Mezzanine Sprinkler Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 2 | 60% | 60% | 100% | 30% | 60%
18043-LM646 08205 | - | DDD |  | Fire Protection System - Ground Floor Fire Hose Cabinet and Fire Extinguisher Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 3 | 60% | 60% | 100% | 30% | 60%
18043-LM646 08206 | - | DDD |  | Fire Protection System - 2nd Floor Fire Hose Cabinet and Fire Extinguisher Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 4 | 60% | 60% | 100% | 30% | 60%
18043-LM646 08207 | - | DDD |  | Fire Protection System - Sections and Details | A |  |  | A0 |  |  | AFC | AFC | KSB | 5 | 60% | 60% | 100% | 30% | 60%
18043-LM646 08301 | - | DDD |  | HVAC System - P&I Diagram | A |  |  | A0 |  |  | AFC | AFC | KSB | 6 | 60% | 60% | 100% | 30% | 60%
18043-LM646 08302 | - | DDD |  | HVAC System - Ground Floor Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 7 | 60% | 60% | 100% | 30% | 60%
18043-LM646 08303 | - | DDD |  | HVAC System - 2nd Floor Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 8 | 60% | 60% | 100% | 30% | 60%
18043-LM646 08304 | - | DDD |  | HVAC System - Section and Details | A |  |  | A0 |  |  | AFC | AFC | KSB | 9 | 60% | 60% | 100% | 30% | 60%
18043-LM646 08501 | - | DDD |  | Fluids System - Ground Floor Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 10 | 60% | 60% | 100% | 30% | 60%
18043-LM646 08502 | - | DDD |  | Fluids System - 2nd Floor Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 11 | 60% | 60% | 100% | 30% | 60%
18043-LM646 08503 | - | DDD |  | Fluids System - Sections and Details | A |  |  | A0 |  |  | AFC | AFC | KSB | 12 | 60% | 60% | 100% | 30% | 60%
18043-LM646 08851 | - | DDD |  | Instrument Datasheets | A |  |  | A0 |  |  | AFC | AFC | KSB | 14 | 60% | 60% | 100% | 30% | 60%
18043-LM646 09301 | - | DDD |  | Control Wiring 1 | A |  |  | A0 |  |  | AFC | AFC | KSB | 16 | 60% | 60% | 100% | 30% | 60%
18043-LM646 09302 | - | DDD |  | Control Wiring 2 | A |  |  | A0 |  |  | AFC | AFC | KSB | 17 | 60% | 60% | 100% | 30% | 60%
Ground Floor Plan EL.+00 , Mezzanine 1A Floor Plan EL.+10.00
|  |  |  | SUB-TOTAL BUILDING NAME OR AREA NAME 1 DRAWINGS |  |  |  | 31
Building Name or Area Name 2
18043-LM190 08210 | - | DDD |  | Fire Protection Plan And Sections | A |  |  | A0 |  |  | AFC | AFC | KSB | 23 | 60% | 60% | 100% | 30% | 60% | LM190 08210 Rv.1 Fire Protection Plan And Sections
18043-LM190 08305 | - | DDD |  | Ground & Second Floor - HVAC Plan and Details | A |  |  | A0 |  |  | AFC | AFC | KSB | 24 | 60% | 60% | 100% | 30% | 60% | LM190 08305 Rv.2 Ground & Second Floor - HVAC Plan and Details
18043-LM191-1 08201 | - | DDD |  | Fire Protection System - Ground Floor Sprinkler Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 26 | 60% | 60% | 100% | 30% | 60% | LM190 08202
18043-LM191-1 08202 | - | DDD |  | Fire Protection System - 2nd Floor Sprinkler Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 27 | 60% | 60% | 100% | 30% | 60% | LM190 08203
18043-LM191-1 08203 | - | DDD |  | Fire Protection System - 3rd Floor Sprinkler Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 28 | 60% | 60% | 100% | 30% | 60% | LM190 08204
18043-LM191-1 08204 | - | DDD |  | Fire Protection System - 4th Floor Sprinkler Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 29 | 60% | 60% | 100% | 30% | 60% | LM190 08205
18043-LM191-1 08205 | - | DDD |  | Fire Protection System - Ground Floor Fire Hose Cabinet and Fire Extinguisher Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 30 | 60% | 60% | 100% | 30% | 60% | LM190 08206
18043-LM191-1 08206 | - | DDD |  | Fire Protection System - 2nd Floor Fire Hose Cabinet and Fire Extinguisher Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 31 | 60% | 60% | 100% | 30% | 60% | LM190 08207
18043-LM191-1 08207 | - | DDD |  | Fire Protection System - 3rd Floor Fire Hose Cabinet and Fire Extinguisher Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 32 | 60% | 60% | 100% | 30% | 60% | LM190 08208
18043-LM191-1 08208 | - | DDD |  | Fire Protection System - 4th Floor Fire Hose Cabinet and Fire Extinguisher Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 33 | 60% | 60% | 100% | 30% | 60% | LM190 08209
18043-LM191-1 08209 | - | DDD |  | Fire Protection System - Roof Floor Fire Hose Cabinet and Fire Extinguisher Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 34 | 60% | 60% | 100% | 30% | 60% | LM190 08210
18043-LM191-1 08210 | - | DDD |  | Fire Protection System - Sections and Details | A |  |  | A0 |  |  | AFC | AFC | KSB | 35 | 60% | 60% | 100% | 30% | 60% | LM190 08210
18043-LM191-1 08301 | - | DDD |  | HVAC System - P&I Diagram | A |  |  | A0 |  |  | AFC | AFC | KSB | 36 | 60% | 60% | 100% | 30% | 60% | LM191 08301
18043-LM191-1 08302 | - | DDD |  | HVAC System - Ground Floor Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 37 | 60% | 60% | 100% | 30% | 60% | LM191 08303
18043-LM191-1 08303 | - | DDD |  | HVAC System - 2nd Floor Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 38 | 60% | 60% | 100% | 30% | 60% | LM191 08304
18043-LM191-1 08304 | - | DDD |  | HVAC System - 3rd Floor Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 39 | 60% | 60% | 100% | 30% | 60% | LM191 08305
18043-LM191-1 08305 | - | DDD |  | HVAC System - 4th Floor Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 40 | 60% | 60% | 100% | 30% | 60% | LM191 08306
18043-LM191-1 08306 | - | DDD |  | HVAC System - Roof Floor Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 41 | 60% | 60% | 100% | 30% | 60% | LM191 08307
18043-LM191-1 08307 | - | DDD |  | HVAC System - Sections and Details | A |  |  | A0 |  |  | AFC | AFC | KSB | 42 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 08501 | - | DDD |  | Fluids System - Plans | A |  |  | A0 |  |  | AFC | AFC | KSB | 43 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 08502 | - | DDD |  | Fluids System - Sections and Details | A |  |  | A0 |  |  | AFC | AFC | KSB | 44 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 09301 | - | DDD |  | Control Wiring 1 exhaust fan (relocation) | A |  |  | A0 |  |  | AFC | AFC | KSB | 46 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 09302 | - | DDD |  | Control Wiring 2 pressurized fan | A |  |  | A0 |  |  | AFC | AFC | KSB | 47 | 60% | 60% | 100% | 30% | 60%
18043-LM191-1 08851 | - | DDD |  | Instrument Datasheets | A |  |  | A0 |  |  | AFC | AFC | KSB | 49 | 60% | 60% | 100% | 30% | 60%
|  |  |  | SUB-TOTAL BUILDING NAME OR AREA NAME 2 DRAWINGS |  |  |  | 24
Building Name or Area Name 3
18043-LM520 08209 | - | DDD |  | Roof Plan | A |  |  | A0 |  |  | AFC | AFC | KSB | 55 | 60% | 60% | 100% | 30% | 60% | LM520 08209 Rv.3 Roof Plan
18043-LM520 08210 | - | DDD |  | Intermediate Plan & Section | A |  |  | A0 |  |  | AFC | AFC | KSB | 56 | 60% | 60% | 100% | 30% | 60% | LM520 08210 Rv.2 Intermediate Plan & Section
[14 empty] | 1106 | 59.62% | 59.7% | 100% | 30.71% | 60.27%
|  |  |  | SUB-TOTAL BUILDING NAME OR AREA NAME 3 DRAWINGS |  |  |  | 2
|  |  |  | GRAND-TOTAL MECHANICAL DRAWINGS |  |  |  | 75
OWNER'S LOGO

## 5. ELECTRICAL
PROJECT NAME LOCATION, PROVINCE, THAILAND
5. ELECTRICAL | [10 empty] | Responsible
| Drawing List | [9 empty] | Leader | Execute | Draftman | DD weight | 50DD |  | 100DD |  | Total Progress
Drawing number |  |  | Descriptions |  | Rv. |  |  | Size | type | Remark |  |  |  |  | Plan | Actual | Plan | Actual
[5 empty] | dd MMM | dd MMM | dd MMM
General Drawing
18043-LMBMS 09017 | - | DDD |  | Electrical Legend and Symbols | A | [5 empty] | AFC | AFC | KSB | 1 | 80% | 80% | 100% | 95% | 95% | LMBMS 09017 Rv.16B Electrical Legend and Symbols
18043-LMBMS 09026 | - | DDD |  | Electrical Typical Details Sheet 1 | A | [5 empty] | AFC | AFC | KSB | 1.5 | 60% | 60% | 100% | 90% | 90% | LMBMS 09026 Rv.A Electrical Typical Details Sheet 1
18043-LMBMS 09027 | - | DDD |  | Electrical Typical Details Sheet 2 | A | [5 empty] | AFC | AFC | KSB | 1.5 | 60% | 60% | 100% | 90% | 90% | LMBMS 09027 Rv.A Electrical Typical Details Sheet 2
18043-LMBMS 09028 | - | DDD |  | Electrical Typical Details Sheet 3 | A | [5 empty] | AFC | AFC | KSB | 1.5 | 60% | 20% | 100% | 90% | 90% | LMBMS 09028 Rv.A Electrical Typical Details Sheet 3
18043-LMBMS 09029 | - | DDD |  | Electrical Typical Details Sheet 4 | A | [5 empty] | AFC | AFC | KSB | 2.5 | 60% | 20% | 100% | 90% | 90% | LMBMS 09029 Rv.A Electrical Typical Details Sheet 4
18043-LMBMS 09030 | - | DDD |  | Electrical Typical Details Sheet 5 | A | [5 empty] | AFC | AFC | KSB | 3.5 | 60% | 20% | 100% | 90% | 90% | LMBMS 09030 Rv.A Electrical Typical Details Sheet 5
18043-LMBMS 09031 | - | DDD |  | Lighting Specification | A | [5 empty] | AFC | NPM | KSB | 2.5 | 80% | 60% | 100% | 90% | 90% | LMBMS 09031 Rv.A Lighting Specification
18043-LM000 09558 | - | DDD |  | General Electrical Work - Cable Tray Layout For B.191 (Modification) | A | [5 empty] | AFC | NPM | KSB | 2.5 | 80% | 70% | 100% | 80% | 80% | LM000 09558 Rv.1 General Electrical Work - Cable Tray Layout For B.191 (Modification)
18043-LM000 09577 | - | DDD |  | Main feeder layout plan 646 Building | A | [5 empty] | AFC | NPM | KSB | 3.5 | 80% | 70% | 100% | 80% | 80% | LM000 09577 Rv.A Main feeder layout plan 646 Building
18043-LM000 09578 | - | DDD |  | Main feeder layout plan 191-1 Building | A | [5 empty] | AFC | NPM | KSB | 4.5 | 80% | 70% | 100% | 80% | 80% | LM000 09578 Rv.A Main feeder layout plan 191-1 Building
18043-LM000 09579 | - | DDD |  | Main feeder layout plan 190 D xxx | A | [5 empty] | AFC | NPM | KSB | 5.5 | 80% | 70% | 100% | 80% | 80% | LM000 09579 Rv.A Main feeder layout plan 190 D xxx
|  |  |  | SUB-TOTAL GENERAL DRAWING DRAWINGS |  |  |  | 11
Building Name or Area Name 1
18043-LM646 09101 | - | DDD |  | List of Lighting Requirement | A | [5 empty] | AFC | NPM | KSB | 1.5 | 0% | 0% | 100% | 30% | 30% | LM646 09101 Rv.A List of Lighting Requirement
18043-LM646 09102 |  | DDD |  | 1st Floor Lighting Plan | A | [5 empty] | AFC | NPM | KSB | 0.5 | 0% | 0% | 100% | 30% | 30% | LM646 09102 Rv.A 1st Floor Lighting Plan
18043-LM646 09103 |  | DDD |  | 1st Floor Mezzanine Lighting Plan | A | [5 empty] | AFC | NPM | KSB | 1.5 | 0% | 0% | 100% | 30% | 30% | LM646 09103 Rv.A 1st Floor Mezzanine Lighting Plan
18043-LM646 09104 |  | DDD |  | 2nd Floor Lighting Plan | A | [5 empty] | AFC | PTF | PMO | 1 | 30% | 30% | 100% | 80% | 80% | LM646 09104 Rv.A 2nd Floor Lighting Plan
18043-LM646 09105 |  | DDD |  | 2nd Floor Mezzanine Lighting Plan | A | [5 empty] | AFC | PTF | PMO | 2 | 30% | 30% | 100% | 80% | 80% | LM646 09105 Rv.A 2nd Floor Mezzanine Lighting Plan
18043-LM646 09106 |  | DDD |  | 1st Floor Emergency Light and Exit Light Plan | A | [5 empty] | AFC | PTF | PMO | 3 | 30% | 30% | 100% | 80% | 80% | LM646 09106 Rv.A 1st Floor Emergency Light and Exit Light Plan
18043-LM646 09107 |  | DDD |  | 1st Floor Mezzanine Emergency Light and Exit Light Plan | A | [5 empty] | AFC | PTF | PMO | 4 | 30% | 30% | 100% | 80% | 80% | LM646 09107 Rv.A 1st Floor Mezzanine Emergency Light and Exit Light Plan
18043-LM646 09108 |  | DDD |  | 2nd Floor Emergency Light and Exit Light Plan | A | [5 empty] | AFC | PTF | PMO | 5 | 30% | 30% | 100% | 80% | 80% | LM646 09108 Rv.A 2nd Floor Emergency Light and Exit Light Plan
18043-LM646 09109 |  | DDD |  | 2nd Floor Mezzanine Emergency Light and Exit Light Plan | A | [5 empty] | AFC | PTF | PMO | 6 | 30% | 30% | 100% | 80% | 80% | LM646 09109 Rv.A 2nd Floor Mezzanine Emergency Light and Exit Light Plan
18043-LM646 09110 |  | DDD |  | 1st Floor Receptacle and Power Supply Plan | A | [5 empty] | AFC | PTF | PMO | 7 | 30% | 30% | 100% | 80% | 80% | LM646 09110 Rv.A 1st Floor Receptacle and Power Supply Plan
18043-LM646 09111 |  | DDD |  | 1st Floor Mezzanine Receptacle and Power Supply Plan | A | [5 empty] | AFC | NPM | KSB | 1.5 | 60% | 60% | 100% | 80% | 80% | LM646 09111 Rv.A 1st Floor Mezzanine Receptacle and Power Supply Plan
18043-LM646 09112 |  | DDD |  | 2nd Floor Receptacle and Power Supply Plan | A | [5 empty] | AFC | NPM | KSB | 2.5 | 60% | 60% | 100% | 80% | 80% | LM646 09112 Rv.A 2nd Floor Receptacle and Power Supply Plan
18043-LM646 09113 |  | DDD |  | 2nd Floor Mezzanine Receptacle and Power Supply Plan | A | [5 empty] | AFC | NPM | KSB | 3.5 | 60% | 60% | 100% | 80% | 80% | LM646 09113 Rv.A 2nd Floor Mezzanine Receptacle and Power Supply Plan
18043-LM646 09201 |  | DDD |  | 1st Floor Fire Alarm Plan | A | [5 empty] | AFC | NPM | KSB | 4.5 | 60% | 60% | 100% | 80% | 80% | LM646 09201 Rv.A 1st Floor Fire Alarm Plan
18043-LM646 09202 |  | DDD |  | 1st Floor Mezzanine Fire Alarm Plan | A | [5 empty] | AFC | NPM | KSB | 1.5 | 60% | 0% | 100% | 90% | 90% | LM646 09202 Rv.A 1st Floor Mezzanine Fire Alarm Plan
18043-LM646 09203 |  | DDD |  | 2nd Floor Fire Alarm Plan | A | [5 empty] | AFC | NPM | KSB | 1 | 0% | 0% | 100% | 30% | 30% | LM646 09203 Rv.A 2nd Floor Fire Alarm Plan
18043-LM646 09204 |  | DDD |  | 2nd Floor Mezzanine Fire Alarm Plan | A | [5 empty] | AFC | NPM | KSB | 2 | 0% | 0% | 100% | 30% | 30% | LM646 09204 Rv.A 2nd Floor Mezzanine Fire Alarm Plan
18043-LM646 09401 |  | DDD |  | 1st Floor Telephone, and Data Network Plan | A | [5 empty] | AFC | NPM | KSB | 3 | 0% | 0% | 100% | 30% | 30% | LM646 09401 Rv.A 1st Floor Telephone, and Data Network Plan
18043-LM646 09402 |  | DDD |  | 1st Floor Mezzanine Telephone, and Data Network Plan | A | [5 empty] | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 95% | 95% | LM646 09402 Rv.A 1st Floor Mezzanine Telephone, and Data Network Plan
18043-LM646 09403 |  | DDD |  | 2nd Floor Telephone, and Data Network Plan | A | [5 empty] | AFC | AFC | KSB | 2 | 60% | 60% | 100% | 95% | 95% | LM646 09403 Rv.A 2nd Floor Telephone, and Data Network Plan
18043-LM646 09404 |  | DDD |  | 2nd Floor Mezzanine Telephone, and Data Network Plan | A | [5 empty] | AFC | AFC | KSB | 1 | 30% | 30% | 100% | 95% | 95% | LM646 09404 Rv.A 2nd Floor Mezzanine Telephone, and Data Network Plan
18043-LM646 09405 |  | DDD |  | 1st Floor Access Control, CCTV Plan | A | [5 empty] | AFC | AFC | KSB | 2 | 30% | 30% | 100% | 95% | 95% | LM646 09405 Rv.A 1st Floor Access Control, CCTV Plan
18043-LM646 09406 |  | DDD |  | 1st Floor Mezzanine Access Control, CCTV Plan | A | [5 empty] | AFC | AFC | KSB | 3 | 30% | 30% | 100% | 95% | 95% | LM646 09406 Rv.A 1st Floor Mezzanine Access Control, CCTV Plan
18043-LM646 09407 |  | DDD |  | 2nd Floor Access Control, CCTV Plan | A | [5 empty] | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 95% | 95% | LM646 09407 Rv.A 2nd Floor Access Control, CCTV Plan
18043-LM646 09408 |  | DDD |  | 2nd Floor Mezzanine Access Control, CCTV Plan | A | [5 empty] | AFC | AFC | KSB | 1 | 30% | 60% | 100% | 95% | 95% | LM646 09408 Rv.A 2nd Floor Mezzanine Access Control, CCTV Plan
18043-LM646 09409 |  | DDD |  | 1st Floor Monitoring Plan | A | [5 empty] | AFC | AFC | KSB | 2 | 30% | 60% | 100% | 95% | 95% | LM646 09409 Rv.A 1st Floor Monitoring Plan
18043-LM646 09410 |  | DDD |  | 1st Floor Mezzanine Monitoring Plan | A | [5 empty] | AFC | AFC | KSB | 3 | 30% | 60% | 100% | 95% | 95% | LM646 09410 Rv.A 1st Floor Mezzanine Monitoring Plan
18043-LM646 09411 |  | DDD |  | 2nd Floor Monitoring Plan | A | [5 empty] | AFC | AFC | KSB | 1 | 30% | 0% | 100% | 30% | 30% | LM646 09411 Rv.A 2nd Floor Monitoring Plan
18043-LM646 09412 |  | DDD |  | 2nd Floor Mezzanine Monitoring Plan | A | [5 empty] | AFC | AFC | KSB | 2 | 30% | 0% | 100% | 30% | 30% | LM646 09412 Rv.A 2nd Floor Mezzanine Monitoring Plan
18043-LM646 09501 |  | DDD |  | Single Line, and Sub Single Line Diagram | A | [5 empty] | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 95% | 95% | LM646 09501 Rv.A Single Line, and Sub Single Line Diagram
18043-LM646 09502 |  | DDD |  | 1st Floor Power Distribution Plan | A | [5 empty] | AFC | AFC | KSB | 2 | 60% | 60% | 100% | 95% | 95% | LM646 09502 Rv.A 1st Floor Power Distribution Plan
18043-LM646 09503 |  | DDD |  | 1st Floor Mezzanine Power Distribution Plan | A | [5 empty] | AFC | AFC | KSB | 1 | 60% | 60% | 100% | 30% | 60% | LM646 09503 Rv.A 1st Floor Mezzanine Power Distribution Plan
18043-LM646 09504 |  | DDD |  | 2nd Floor Power Distribution Plan | A | [5 empty] | AFC | AFC | KSB | 2 | 60% | 60% | 100% | 30% | 60% | LM646 09504 Rv.A 2nd Floor Power Distribution Plan
18043-LM646 09505 |  | DDD |  | 2nd Floor Mezzanine Power Distribution Plan | A | [5 empty] | AFC | AFC | KSB | 3 | 60% | 60% | 100% | 30% | 60% | LM646 09505 Rv.A 2nd Floor Mezzanine Power Distribution Plan
18043-LM646 09701 |  | DDD |  | Lightning Protection System Plan | A | [5 empty] | AFC | AFC | KSB | 4 | 60% | 60% | 100% | 30% | 60% | LM646 09701 Rv.A Lightning Protection System Plan
18043-LM646 09702 |  | DDD |  | Grounding System Plan | A | [5 empty] | AFC | AFC | KSB | 5 | 60% | 60% | 100% | 30% | 60% | LM646 09702 Rv.A Grounding System Plan
|  |  |  | SUB-TOTAL BUILDING NAME OR AREA NAME 1 DRAWINGS |  |  |  | 36
Building Name or Area Name 2
18043-LM191-1 09101 | - | DDD |  | List of Lighting Requirement | A | [5 empty] | AFC | AFC | KSB | 11 | 60% | 60% | 100% | 30% | 60% | LM191-1 09101 Rv.A List of Lighting Requirement
18043-LM191-1 09102 | - | DDD |  | Ground and 2nd Floor Lighting, Emergency Light and Exit Light Plans | A | [5 empty] | AFC | AFC | KSB | 12 | 60% | 60% | 100% | 30% | 60% | LM191-1 09102 Rv.A Ground and 2nd Floor Lighting, Emergency Light and Exit Light Plans
18043-LM191-1 09103 | - | DDD |  | 3rd and Roof Floor Lighting, Emergency Light and Exit Light Plans | A | [5 empty] | AFC | AFC | KSB | 13 | 60% | 60% | 100% | 30% | 60% | LM191-1 09103 Rv.A 3rd and Roof Floor Lighting, Emergency Light and Exit Light Plans
18043-LM191-1 09201 | - | DDD |  | Fire Alarm System Diagram, Ground and 2nd Floor Fire Alarm Plans | A | [5 empty] | AFC | AFC | KSB | 14 | 60% | 60% | 100% | 30% | 60% | LM191-1 09201 Rv.A Fire Alarm System Diagram, Ground and 2nd Floor Fire Alarm Plans
18043-LM191-1 09202 | - | DDD |  | 3rd and Roof Floor Fire Alarm Plans | A | [5 empty] | AFC | AFC | KSB | 15 | 60% | 60% | 100% | 30% | 60% | LM191-1 09202 Rv.A 3rd and Roof Floor Fire Alarm Plans
18043-LM191-1 09401 | - | DDD |  | Telephone, and Data Network Plan | A | [5 empty] | AFC | AFC | KSB | 16 | 60% | 60% | 100% | 30% | 60% | LM191-1 09401 Rv.A Telephone, and Data Network Plan
18043-LM191-1 09402 | - | DDD |  | Access Control, Monitoring and CCTV Plan | A | [5 empty] | AFC | AFC | KSB | 17 | 60% | 60% | 100% | 30% | 60% | LM191-1 09402 Rv.A Access Control, Monitoring and CCTV Plan
18043-LM191-1 09501 | - | DDD |  | Single Line Diagram, Ground and 2nd Floor Receptacle and Power Supply Plans | A | [5 empty] | AFC | AFC | KSB | 18 | 60% | 60% | 100% | 30% | 60% | LM191-1 09501 Rv.A Single Line Diagram, Ground and 2nd Floor Receptacle and Power Supply Plans
18043-LM191-1 09502 | - | DDD |  | 3rd and Roof Floor Receptacle and Power Supply Plans | A | [5 empty] | AFC | AFC | KSB | 19 | 60% | 60% | 100% | 30% | 60% | LM191-1 09502 Rv.A 3rd and Roof Floor Receptacle and Power Supply Plans
18043-LM191-1 09701 | - | DDD |  | Lightning Protection System and Grounding System Plans | A | [5 empty] | AFC | AFC | KSB | 20 | 60% | 60% | 100% | 30% | 60% | LM191-1 09701 Rv.A Lightning Protection System and Grounding System Plans
|  |  |  | SUB-TOTAL BUILDING NAME OR AREA NAME 2 DRAWINGS |  |  |  | 10
Building Name or Area Name 3
18043-LM520 09103 | - | DDD |  | Lighting Plan (Modification) | A | [5 empty] | AFC | AFC | KSB | 26 | 60% | 60% | 100% | 30% | 60% | LM520 09103 Rv.5 Lighting Plan (Modification)
18043-LM520 09201 | - | DDD |  | Fire Alarm Plans | A | [5 empty] | AFC | AFC | KSB | 27 | 60% | 60% | 100% | 30% | 60% | LM520 09201 Rv.3 Fire Alarm Plans
18043-LM520 09505 | - | DDD |  | Modification Cable Tray and Conduit Plan | A | [5 empty] | AFC | AFC | KSB | 28 | 60% | 60% | 100% | 30% | 60% | LM520 09505 Rv.A Modification Cable Tray and Conduit Plan
|  |  |  | SUB-TOTAL BUILDING NAME OR AREA NAME 3 DRAWINGS |  |  |  | 3
|  |  |  | GRAND-TOTAL ELECTRICAL DRAWINGS |  |  |  | 60
[14 empty] | 354 | 55.85% | 45.25% | 77.97% | 26.88% | 65.31%
OWNER'S LOGO

## Eng name
| ตรวจสอบความถูกต้องแล้ว | prof. id | ชื่อ-สกุล | English Name
Arch
|  | ว-สถ. 607 | อัญชลี เหล่าบุญเจริญ | UNCHARLEE LAOBOONCHAROEN
| Drawing List | ภ-สถ. 22586 | ภาคภูมิ แก้วมี | PARKPOOM KAEWMEE
|  | ภ-สถ. 25517 | ปวีณา ธนวุฒิจิราวัชร | PAWEENA THANAWUTCHIRAWAT
Structural
|  | สย. 9776 | พิชิต ผาติเวทย์ | PICHIT PHATIWET
|  | สย.10758 | ณภัค ศรีบุญเรือง | NAPAK SRIBOONRUENG
|  | ภย.53735 | พิมพ์ประภา ขวัญพ่วง | PIMPRAPA KHWANPUANG
|  | ภย.74343 | เขมทัต ธนะชัย | KHEMMATAT THANACHAI
|  | ภย.89064 | ธนาธิป กลิ่นเฟื่อง | THANATHIP KLINFUEANG
|  |  | จิรวัฒน์ คชบก | CHIRAWAT KOCHABOG
Civil
|  | ภย.75757 | อัรฟาน เจะอาลี | ARFARN CHEALI
Mech.
|  | สก. 3504 | คชฤทธิ์ จ่างพิพัฒน์นวกิจ | KOTCHARIT JANGPIPATNAVAKIT
|  | ภก. 45707 | กิตติพศ พูนเต็ม | KITTIPOT POONTEM
|  | ภก. 52671 | ธิติวุฒิ สุวรรณคาม | THITIWUT SUWANNAKAM
|  | ภก. 54219 | คาวี ศรีเงิน | KAWEE SRINGOEN
|  | ภก. 57198 | พันธิตร โลหกิจ | PANTHID LOHAKIT
Elec.
|  | วฟก. 993 | ศุภชัย ลิมปนากร | SUPACHAI LIMPANAKORN
|  | ภฟก. 63154 | เกียรติศักดิ์ วงศ์พานิช | KIATTISAK VONGPHANICH
|  | ภฟก. 67684 | กฤติน สิริโภคากร | KRITTIN SIRIPOKAKORN
|  | ภฟก. 67463 | ภูริภัทร์ อัศวภิญโญชัย | PURIPHAT ASAWAPINYOCHAI
|  | ภฟก. 68732 | ณัฐพัชร์ เหล่ากาญจนอุดม | NATTAPAT LAOKRANJANAUDOM
Sanitary
|  | ภส. 1034 | คชฤทธิ์ จ่างพิพัฒน์นวกิจ | KOTCHARIT JANGPIPATNAVAKIT

## Numbering System
Project : LMC PF1 ROR
Owner : Michelin Laemchabang
DRAWING NUMBERING CONTROL (Drawing no.)
Drawing List |  | Factory |  | Bldg No. | Discipline / number |  | Phase
18043 | - | LM |  | XXX | XXXXX | - | XXX
DRAWING NUMBERING CONTROL (File name)
Proj Number |  | Factory |  | Bldg No. | Discipline / number |  | Phase |  | Revision | Drawing name
18043 | - | LM |  | XXX | XXXXX | - | XXX | - | A | XXX
Drawing no. |  | 18043-LM000 01105-DDD
File Name |  | 180430-LM000 01105-DDD-A Plot plan
Proj. Number |  | 18043
กรณีแบบที่ทำต่อๆๆๆๆ กันเลขหมด หรืออะไรก็ตาม
Factory |  | LM |  |  |  |  | ไม่ต้องรันเลขต่อก็ได้ (แบบที่ปกติเราทำ)
ให้ใช้เลขซ้ำได้เลย
เพราะเรามีเลขโปรเจคอยู่แล้ว ไม่ซ้ำแน่นอน
Area |  | 646 |  | ASRS Building
|  | wait MSC |  | Curing office & Workshop
|  | 520 |  | Cold Preparation Workshop
|  | 561 |  | TBM Workshop
|  | 191 |  | After Curing Workshop
|  | 642 |  | Modification of Hot Water Improvement
|  | BME |  | Code used for drawing showing several buildings
|  | BMS |  | Code used for standard details ( Typical detail)
Discipline |  | Use michelin Code
Phase |  | Detailed Design | - | DDD
|  | For Construction | - | IFC
|  | As-built | - | ASB
Revision |  | Basic & Detail Design & Bidding & Permit
A, B, C, ….
Notes |  | กรณีเอาแบบ Detailed Design มาทำรายละเอียดเพิ่มเพื่อออก Permit ให้เติม -P ไว้ด้านหลัง (น่าจะมีแค่แบบ Architect)
SAMPLE

## Subcover
LMC PF1 ROR PROJECT LAEM CHABANG CHONBURI, THAILAND
Drawing List
0. CIVIL WORKS
LMC PF1 ROR PROJECT LAEM CHABANG CHONBURI, THAILAND
1. ARCHITECTURAL WORKS
LMC PF1 ROR PROJECT LAEM CHABANG CHONBURI, THAILAND
2. STRUCTURAL WORKS
LMC PF1 ROR PROJECT LAEM CHABANG CHONBURI, THAILAND
3. MECHANICAL WORKS
LMC PF1 ROR PROJECT LAEM CHABANG CHONBURI, THAILAND
4. ELECTRICAL WORKS
SAMPLE (OPTIONAL)